## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 49
PROJECT NAME | Wave Diaries
PROJECT MENTOR (sponsor) | Karan Nijhawan
TEAM MEMBERS | Aditya Gaur
Shivam Gupta
Raunak Seksaria
Manit Roy

## Status
PROJECT NUMBER | 49
PROJECT NAME | Wave Diaries
PROJECT MENTOR (sponsor) | Karan Nijhawan
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21) Project Not Allocated
Week 2 (January 22 - January 28)
Learn Express JS and node js | Preparation | Aditya | 5 | 4.5 | Done | Tech stack required for backend | 0.5 | 11.1111
GIT Repository setup | Preparation | Raunak | 0.25 | 0.25 | Done | Project Management Tool | 0 | 0
MoM-1 | Documentation | Raunak | 0.5 | 0.75 | Done | Recalled meeting details and documented them | -0.25 | 33.3333
Learn React | Preparation | Shivam | 4 | 5 | Done | Learning react is necessary for front end development | -1 | 20
Team Meeting | Coordination | Aditya, Manit, Raunak, Shivam | 1 | 2 | Done | Discussed initial ideas about project | -1 | 50
Status tracker | Documentation | Aditya | 1 | 1 | Done | Tracking work documentation | 0 | 0
Client Meeting-1 | Requirements | Aditya, Manit, Raunak, Shivam | 0.5 | 0.5 | Done | Met the client for the first time | 0 | 0
Tried out API Calls | Preparation | Manit | 1 | 0.75 | Done | Tried out OpenAI's Whisper API Calls | 0.25 | 33.3333
Week 3 (January 29 - February 2)
Project Synopsis | Documentation | Aditya, Raunak | 1.5 | 2.5 | Done | Initial synopsis | -1 | 40
Project Plan | Documentation | Shivam | 2 | 2 | Done | Initial plan | 0 | 0
User Usage Flowchart | Design | Shivam | 2 | 1.5 | Done | Design for better management and clarity | 0.5 | 33.3333
Status tracker | Documentation | Aditya, Raunak | 1 | 1 | Done | Tracking work documentation | 0 | 0
Reading Tasks | Requirements | Raunak, Manit | 4 | 4.5 | Done | Client assigned work | -0.5 | 11.1111
Team Meeting | Coordination | Aditya, Manit, Raunak, Shivam | 1 | 2 | Done | Discussed tech stack to be used, discussed requirements, discussed team roles(rough) | -1 | 50
Learn Figma and React Basics | Preparation | Raunak | 3 | 3.5 | Done | Required for UI/UX design | -0.5 | 14.2857
Read about RAG | Preparation | Manit | 2.5 | 2 | Done | Read about long-term memory for LLMs | 0.5 | 25
Meet Scheduling | Coordination | Raunak | 0.25 | 0.25 | Done | Weekly meets schedule | 0 | 0
Client Meeting-2 | Requirements | Aditya, Manit, Raunak, Shivam | 0.5
Client Meet- Tracking weekly work | Coordination | Aditya, Manit, Raunak, Shivam | 0.5
Week 4 (February 3 - February 9)
Learning Scrum master basics | Preparation | Raunak | 2.5 | 3 | Done | Task assigned by Client | -0.5 | 16.6667
Learning Trello | Coordination | Raunak | 2 | 2 | Done | Task assigned by Client | 0 | 0
Introduction to Neural Networks | Preparation | Manit | 3 | 3 | Done | Learning from youtube channel 3blue1brown | 0 | 0
Google AI - Intro to ML | Preparation | Manit | 4 | 4 | Done | Basics for ML | 0 | 0
Learning NLP | Preparation | Manit | 1 | 1 | Done |  | 0 | 0
Learning Git | Preparation | Aditya,Raunak | 3 | 3 | Done |  | 0 | 0
Learning DevOps Fundamentals | Preparation | Aditya | 2 | 2 | Done |  | 0 | 0
Learning WebDev | Preparation | Shivam | 3 | 3 | Done |  | 0 | 0
Learning React | Preparation | Shivam | 4 | 4 | Done |  | 0 | 0
Learning MongoDB | Preparation | Aditya | 3 | 3 | Done |  | 0 | 0
Machine Learning (Supervised Learning) | Preparation | Raunak | 3 | 3 | Done | Coursera : "Machine Learning " by Angrew Ng | 0 | 0
MoM | Documentation | Aditya | 1 | 1 | Done |  | 0 | 0
Week 5 (February 10- February 16)
Team Meeting | Coordination | Aditya, Manit, Raunak, Shivam | 6 | 5 | Done | Role assignment finalised according to client specifications | 1 | 20
Setting up Trello | Design | Raunak | 0.5 | 0.75 | Done | Client specified project tracker | -0.25 | 33.3333
Read about Scrum | Design | Raunak | 1.5 | 2 | Done |  | -0.5 | 25
Introduction to NLTK | Preparation | Manit | 2.5 | 3 | Done |  | -0.5 | 16.6667
Hugging Face course | Preparation | Manit | 4.5 | 5 | Done |  | -0.5 | 10
SRS | Documentation | Raunak | 3 | 3 | Done |  | 0 | 0
Set up figma and begin design | Design | Shivam | 3.5 | 4 | Done |  | -0.5 | 12.5
Learn encryption Basics | Preparation | Aditya | 4 | 4 | Done |  | 0 | 0
Read about Unit Testing | Preparation | Shivam, Aditya | 4.25 | 4 | Done |  | 0.25 | 6.25
Read about TypeScript and ESLint | Preparation | Shivam, Aditya | 4 | 4 | Done |  | 0 | 0
Project plan v2 | Documentation | Raunak | 2 | 2 | Done |  | 0 | 0
Project concept v2 | Documentation | Raunak | 0.75 | 1.5 | Ongoing |  | -0.75 | 50
Use Cases dressing (part of SRS) | Documentation | Manit, Shivam, Raunak | 5 |  | Done
Status tracker | Documentation | Raunak | 1.5 |  | Done
Week 6 (February 17- February 23)
Client meet | Coordination | Aditya, Manit, Raunak, Shivam | 2 | 8 | Done | met for 30 mins this week because that was sufficient | -6 | 75
Team Meeting | Coordination | Aditya, Manit, Raunak, Shivam | 0 | 4 | Delayed | didnt require a team meet this week, not much to discuss | -4 | 100
Read about scrum processes | Preparation | Raunak | 1.25 | 1.5 | Done |  | -0.25 | 16.6667
Use trello in action | Coordination | Raunak | 0.5 | 1 | Done |  | -0.5 | 50
Read about langchain | Preparation | Raunak | 4 | 4 | Done |  | 0 | 0
Status tracker | Documentation | Raunak | 0.5 | 0.5 | Done |  | 0 | 0
Explore Next.js and Remix as possible react frameworks | Preparation | Shivam | 5.25 | 5 | Done |  | 0.25 | 5
Read about RAG newer advances | Preparation | Manit | 2 | 2 | Done |  | 0 | 0
Read about ethical AI guidelines | Preparation | Manit | 1.25 | 1.5 | Done |  | -0.25 | 16.6667
Read about CI/CD pipeline | Preparation | Manit, Aditya | 4.75 | 5 | Done |  | -0.25 | 5
Read about aws basics | Preparation | Aditya | 3.25 | 3 | Done |  | 0.25 | 8.3333
Read about AiC | Preparation | Aditya | 2 | 2 | Done |  | 0 | 0
MoM | Documentation | Manit | 0.25 | 0.5 | Done
Week 7 (Februaru 24-March 2) | [5 empty] | midsem week, lesser work done, no client or team meet
Status tracker | Documentation | Raunak | 0.25 | 0.25 | Done |  | 0 | 0
Update SRS | Documentation | Raunak | 0 | 1 | Delayed |  | -1 | 100
Reading API call documentation | Preparation | Raunak, Manit | 4.5 | 4 | Done |  | 0.5 | 12.5
Read about Docker and Kubernetes | Preparation | Aditya | 3.75 | 3.5 | Done | production environment | 0.25 | 7.1429
Read about Terraform | Preparation | Manit | 1.5 | 1.5 | Done |  | 0 | 0
Encryption techniques | Preparation | Shivam | 3.5 | 3.5 | Done |  | 0 | 0
Team Meeting | Coordination | Aditya, Manit, Raunak, Shivam | 1 |  | Done
Week 8 (March 3-March 9)
Client meet | Coordination | Aditya, Manit, Raunak, Shivam | 4 | 4 | Done |  | 0 | 0
Update SRS | Documentation | Raunak, Shivam | 4 | 3 | Delayed | project use cases changing based on a new idea | 1 | 33.3333
Do initial frontend design | Development | Raunak, Shivam | 5 | 6 | Done |  | -1 | 16.6667
Do backend routing | Development | Aditya, Manit, | 8 | 6 | Done |  | 2 | 33.3333
Build the AI prototype | Development | Manit, Raunak | 8 | 8 | Done |  | 0 | 0
Team Meeting | Coordination | Aditya, Manit, Raunak, Shivam | 4 | 4 | Done |  | 0 | 0
Unit Testing for backend routes | Testing | Aditya, Manit | 4 | 4 | Done |  | 0 | 0
Unit Testing for frontend | Testing | Shivam | 3 | 3 | Done |  | 0 | 0
Design Document | Documentation | Aditya, Shivam | 4 |  | Done
MOM | Documentation | Shivam | 0.25 |  | Done
Status tracker | Documentation | Aditya | 0.25 |  | Done
Week 9 (March 10-March 16)
Client meet | Coordination | Aditya, Raunak, Shivam | 6 | 6 | Done | more since R1 phase | 0 | 0
Build the frontend for the web-app | Development | Shivam, Raunak | 9.5 | 10 | Done |  | -0.5 | 5
Unit Testing for AI | Development | Aditya, Manit | 4.5 | 4 | Done |  | 0.5 | 12.5
Unit Testing for Frontend | Development | Shivam, Raunak | 2.5 | 2 | Done |  | 0.5 | 25
Integration Testing | Development | Manit | 3 | 4 | Ongoing |  | -1 | 25
Status tracker | Documentation | Shivam | 0.25 | 0.25 | Done |  | 0 | 0
MOM | Documentation | Shivam | 0.25 | 0.25 | Done |  | 0 | 0
Code refactoring | Development | Aditya | 2.5 | 3 | Ongoing |  | -0.5 | 16.6667
R1 deployment | Development | Manit, Aditya | 2.5 | 2 | Done | this is for ngrok | 0.5 | 25
Code linting | Development | Raunak | 2 | 2 | Ongoing |  | 0 | 0
User guide/README.md | Documentation | Shivam | 0.5 | 0.5 | Ongoing |  | 0 | 0
Week 10 (March 17-March 23)
Client meet | Coordination | Aditya, Raunak, Shivam, Manit |  | 8 | Planned
Add vaccination features | Development | Raunak |  | 4 | Planned
Add chat history feature | Development | Aditya |  | 5 | Planned
SRS update | Requirements | Shivam, Raunak |  | 5 | Planned
Code review | Testing | Shivam |  | 3 | Planned
Extensive testing | Testing | Manit |  | 5 | Planned
PPT presentation and practice | Delivery | Aditya, Raunak, Shivam, Manit |  | 6 | Planned
Readme, comments and code documentation | Documentation | Manit, Raunak |  | 2 | Planned
Present to client and prof | Delivery | Aditya, Raunak, Shivam, Manit |  | 0.67 | Planned
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically